## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a project team member, I want to upload PDF, DOCX, CSV and TXT documents so that project information can be processed. | Must Have | None | Lalit Aditya | Completed
Sprint 1 | Sprint 1 | US-02 | As a system, I want to extract text from uploaded documents so that the information can be analyzed. | Must Have | US-01 | Lalit Aditya | Completed
Sprint 1 | Sprint 1 | US-03 | As a system, I want to divide documents into meaningful chunks so that relevant information can be retrieved. | Must Have | US-02 | Lalit Aditya | Completed
Sprint 1 | Sprint 1 | US-04 | As a system, I want to generate embeddings for document chunks so that semantic search can be performed. | Must Have | US-03 | Lalit Aditya | Completed
Sprint 1 | Sprint 1 | US-05 | As a system, I want to store document embeddings in a vector database so that project information can be retrieved efficiently. | Must Have | US-04 | Lalit Aditya | Completed
Sprint 1 | Sprint 1 | US-06 | As a user, I want to retrieve relevant project information using semantic search. | Must Have | US-05 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-07 | As a project manager, I want the system to automatically extract project scope and goals from project documents. | Must Have | US-06 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-08 | As a project manager, I want the system to identify project deliverables, milestones and deadlines. | Must Have | US-06 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-09 | As a project manager, I want the system to identify project risks and delivery challenges. | Must Have | US-06 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-10 | As a project manager, I want the system to identify blockers and unresolved issues. | Must Have | US-06 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-11 | As a project manager, I want the system to identify pending decisions and action items. | Should Have | US-10 | Lalit Aditya | Completed
Sprint 2 | Sprint 2 | US-12 | As a system, I want all agent outputs to be returned in structured JSON format. | Must Have | US-07, US-09, US-10 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-13 | As a project manager, I want the system to automatically generate structured project documentation from uploaded project artifacts so that important project information is organized in one place. | Must Have | US-12 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-14 | As a project manager, I want the system to generate relevant user stories from project requirements and documents so that project requirements can be represented in an Agile format. | Must Have | US-13 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-15 | As a project manager, I want the system to generate a structured risk register from identified project risks so that risks can be tracked systematically. | Must Have | US-09, US-13 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-16 | As a project manager, I want the system to extract and organize pending action items from project documents so that unresolved tasks can be tracked. | Must Have | US-11, US-13 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-17 | As a project manager, I want the system to calculate an overall project health score so that I can quickly understand the current project condition. | Must Have | US-07, US-09, US-10 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-18 | As a project manager, I want the system to evaluate scope clarity so that unclear or incomplete project scope can be identified. | Should Have | US-17 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-19 | As a project manager, I want the system to evaluate project timeline health using deadlines and progress information so that potential delivery delays can be identified. | Should Have | US-08, US-17 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-20 | As a project manager, I want the system to evaluate project risk health so that the impact of identified risks on project delivery can be understood. | Should Have | US-09, US-17 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-21 | As a project manager, I want the system to evaluate unresolved blockers so that issues affecting project progress can be highlighted. | Should Have | US-10, US-17 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-22 | As a project team member, I want to ask natural-language questions about my project so that I can quickly retrieve project information. | Must Have | US-06 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-23 | As a project team member, I want the assistant to answer questions using information from uploaded project documents so that responses remain relevant to the project context. | Must Have | US-22, US-06 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-24 | As a project team member, I want the assistant to provide document sources for its answers so that I can verify the information. | Should Have | US-23 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-25 | As a project user, I want documentation, health scoring and conversational intelligence agents to work with the existing RAG pipeline so that all project intelligence features use a unified knowledge base. | Must Have | US-13, US-17, US-22 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-26 | As a project developer, I want to validate the outputs of the Milestone 3 agents so that generated documentation, health scores and assistant responses are reliable and structured. | Must Have | US-15, US-20, US-24 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-27 | As a project user, I want the Milestone 3 agents to be accessible through backend APIs so that the frontend can consume their results. | Must Have | US-13, US-17, US-22 | Lalit Aditya | Completed
Sprint 3 | Sprint 3 | US-28 | As a project user, I want agent results to be presented in structured sections so that project insights are easy to understand. | Must Have | US-27 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-29 | As a project manager, I want a centralized dashboard so that I can view important project insights in one place. | Must Have | US-17, US-22 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-30 | As a project manager, I want to view the overall project health score so that I can quickly understand project status. | Must Have | US-17 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-31 | As a project manager, I want to view identified project risks so that potential delivery problems can be monitored. | Must Have | US-09, US-15 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-32 | As a project manager, I want to view pending action items so that unresolved tasks can be tracked. | Must Have | US-16 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-33 | As a project manager, I want to view the project scope and major deliverables so that I can quickly understand project objectives. | Must Have | US-07, US-14 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-34 | As a project team member, I want to upload new project documents without re-uploading existing documents so that the knowledge base stays current. | Must Have | US-01, US-05 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-35 | As a project team member, I want newly uploaded documents to be processed and added to the knowledge base automatically. | Must Have | US-34 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-36 | As a project manager, I want project insights to reflect newly uploaded information so that analysis remains up to date. | Should Have | US-35, US-29 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-37 | As a developer, I want to test the complete project workflow so that all components work together correctly. | Must Have | US-29, US-35 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-38 | As a developer, I want to test PDF, DOCX, CSV and TXT documents so that the system works across supported document types. | Must Have | US-37 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-39 | As a developer, I want to validate all agent outputs so that generated insights are structured and reliable. | Must Have | US-37 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-40 | As a developer, I want to test different project-related questions so that assistant responses remain relevant and grounded. | Must Have | US-23, US-37 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-41 | As a developer, I want to document the system architecture, technologies and implementation so that the project can be maintained and understood. | Must Have | US-37 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-42 | As a project developer, I want to prepare the final project report so that the implementation, testing and results are formally documented. | Must Have | US-41 | Lalit Aditya | Completed
Sprint 4 | Sprint 4 | US-43 | As a project developer, I want to prepare a final demonstration so that the complete project workflow can be presented. | Must Have | US-29, US-35, US-42 | Lalit Aditya | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T001 | Implement file upload support for PDF, DOCX, CSV and TXT | 2026-08-20 | 2026-08-21 | Lalit Aditya | Development | Completed | 6
US-01 | T002 | Add file type and input validation | 2026-08-21 | 2026-08-22 | Lalit Aditya | Development | Completed | 4
US-02 | T003 | Implement PDF text extraction | 2026-08-22 | 2026-08-24 | Lalit Aditya | Development | Completed | 6
US-02 | T004 | Implement DOCX, CSV and TXT text extraction | 2026-08-24 | 2026-08-26 | Lalit Aditya | Development | Completed | 8
US-02 | T005 | Validate extracted content from different document formats | 2026-08-26 | 2026-08-27 | Lalit Aditya | Testing | Completed | 5
US-03 | T006 | Implement document text cleaning and preprocessing | 2026-08-27 | 2026-08-29 | Lalit Aditya | Development | Completed | 5
US-03 | T007 | Implement recursive document chunking | 2026-08-29 | 2026-08-31 | Lalit Aditya | Development | Completed | 6
US-03 | T008 | Configure chunk size and overlap | 2026-08-31 | 2026-08-31 | Lalit Aditya | Development | Completed | 4
US-04 | T009 | Integrate Sentence Transformer embedding model | 2026-09-01 | 2026-09-01 | Lalit Aditya | Development | Completed | 5
US-04 | T010 | Generate embeddings for document chunks | 2026-09-01 | 2026-09-02 | Lalit Aditya | Development | Completed | 6
US-05 | T011 | Configure ChromaDB vector database | 2026-09-02 | 2026-09-02 | Lalit Aditya | Development | Completed | 5
US-05 | T012 | Store document chunks and embeddings in ChromaDB | 2026-09-02 | 2026-09-03 | Lalit Aditya | Development | Completed | 6
US-06 | T013 | Implement semantic query embedding | 2026-09-03 | 2026-09-03 | Lalit Aditya | Development | Completed | 4
US-06 | T014 | Implement top-k semantic retrieval from vector database | 2026-09-03 | 2026-09-03 | Lalit Aditya | Testing | Completed | 5
SPRINT 2 BACKLOG
US-07 | T015 | Design scope and goal extraction agent | 2026-09-08 | 2026-09-08 | Lalit Aditya | Analysis | Completed | 4
US-07 | T016 | Implement project scope extraction from retrieved context | 2026-09-08 | 2026-09-09 | Lalit Aditya | Development | Completed | 7
US-08 | T017 | Implement milestone and deliverable extraction | 2026-09-09 | 2026-09-10 | Lalit Aditya | Development | Completed | 7
US-08 | T018 | Implement deadline and important-date extraction | 2026-09-10 | 2026-09-10 | Lalit Aditya | Development | Completed | 5
US-09 | T019 | Design risk detection agent | 2026-09-10 | 2026-09-10 | Lalit Aditya | Analysis | Completed | 4
US-09 | T020 | Implement project risk identification | 2026-09-10 | 2026-09-12 | Lalit Aditya | Development | Completed | 8
US-09 | T021 | Implement delivery challenge and dependency-gap detection | 2026-09-12 | 2026-09-13 | Lalit Aditya | Development | Completed | 7
US-10 | T022 | Design blocker identification logic | 2026-09-13 | 2026-09-13 | Lalit Aditya | Analysis | Completed | 4
US-10 | T023 | Implement blocker and unresolved-issue extraction | 2026-09-13 | 2026-09-14 | Lalit Aditya | Development | Completed | 7
US-11 | T024 | Implement pending decision identification | 2026-09-14 | 2026-09-14 | Lalit Aditya | Development | Completed | 5
US-11 | T025 | Implement action-item extraction with owner and status | 2026-09-14 | 2026-09-15 | Lalit Aditya | Development | Completed | 6
US-12 | T026 | Define structured JSON output schemas for agents | 2026-09-15 | 2026-09-15 | Lalit Aditya | Development | Completed | 4
US-12 | T027 | Integrate structured JSON responses across agents | 2026-09-15 | 2026-09-16 | Lalit Aditya | Development | Completed | 6
US-12 | T028 | Validate agent outputs using sample project documents | 2026-09-16 | 2026-09-16 | Lalit Aditya | Testing | Completed | 8
SPRINT 3 BACKLOG
US-13 | T-13 | Design Documentation Generation Agent | 2026-09-17 | 2026-09-18 | Lalit Aditya | Development | Completed | 2
US-14 | T-14 | Implement User Story Generation | 2026-09-18 | 2026-09-19 | Lalit Aditya | Development | Completed | 2
US-15 | T-15 | Implement Risk Register Generation | 2026-09-19 | 2026-09-20 | Lalit Aditya | Development | Completed | 2
US-16 | T-16 | Implement Action Item Generation | 2026-09-20 | 2026-09-21 | Lalit Aditya | Development | Completed | 2
US-17 | T-17 | Design Project Health Scoring Agent | 2026-09-22 | 2026-09-23 | Lalit Aditya | Development | Completed | 2
US-18 | T-18 | Implement Scope Health Analysis | 2026-09-23 | 2026-09-24 | Lalit Aditya | Development | Completed | 2
US-19 | T-19 | Implement Timeline Health Analysis | 2026-09-24 | 2026-09-25 | Lalit Aditya | Development | Completed | 2
US-20 | T-20 | Implement Overall Project Health Score | 2026-09-25 | 2026-09-26 | Lalit Aditya | Development | Completed | 2
US-22 | T-21 | Design Conversational Project Assistant | 2026-09-26 | 2026-09-27 | Lalit Aditya | Development | Completed | 2
US-23 | T-22 | Implement Context-Grounded Q&A | 2026-09-27 | 2026-09-28 | Lalit Aditya | Development | Completed | 2
US-24 | T-23 | Implement Source References | 2026-09-28 | 2026-09-28 | Lalit Aditya | Development | Completed | 1
US-25 | T-24 | Integrate Milestone 3 Agents with RAG Pipeline | 2026-09-29 | 2026-09-29 | Lalit Aditya | Integration | Completed | 2
US-26 | T-25 | Validate and Test Agent Outputs | 2026-09-29 | 2026-09-30 | Lalit Aditya | Testing | Completed | 2
US-27 | T-26 | Integrate Agent APIs with Frontend | 2026-09-30 | 2026-09-30 | Lalit Aditya | Integration | Completed | 1
US-28 | T-27 | Implement Structured Agent Result Display | 2026-09-30 | 2026-09-30 | Lalit Aditya | Frontend Development | Completed | 1
SPRINT 4 BACKLOG
US-29 | T-28 | Design Project Insights Dashboard | 2026-10-01 | 2026-10-02 | Lalit Aditya | Frontend Development | Completed | 2
US-30 | T-29 | Integrate Project Health Score | 2026-10-02 | 2026-10-02 | Lalit Aditya | Frontend Integration | Completed | 1
US-31 | T-30 | Implement Risk Summary Section | 2026-10-03 | 2026-10-03 | Lalit Aditya | Frontend Development | Completed | 1
US-32 | T-31 | Implement Action Items Section | 2026-10-04 | 2026-10-04 | Lalit Aditya | Frontend Development | Completed | 1
US-33 | T-32 | Implement Scope Summary Section | 2026-10-05 | 2026-10-05 | Lalit Aditya | Frontend Development | Completed | 1
US-34 | T-33 | Implement Incremental Document Upload | 2026-10-06 | 2026-10-07 | Lalit Aditya | Backend Development | Completed | 2
US-35 | T-34 | Update Vector Knowledge Base with New Documents | 2026-10-07 | 2026-10-08 | Lalit Aditya | RAG Integration | Completed | 2
US-36 | T-35 | Refresh Project Insights after New Upload | 2026-10-08 | 2026-10-08 | Lalit Aditya | Integration | Completed | 1
US-37 | T-36 | Conduct End-to-End System Testing | 2026-10-09 | 2026-10-10 | Lalit Aditya | Testing | Completed | 2
US-38 | T-37 | Test PDF, DOCX, CSV and TXT Workflows | 2026-10-10 | 2026-10-11 | Lalit Aditya | Testing | Completed | 2
US-39 | T-38 | Validate Agent Outputs | 2026-10-11 | 2026-10-12 | Lalit Aditya | Testing | Completed | 1
US-40 | T-39 | Test Conversational Assistant Workflows | 2026-10-12 | 2026-10-13 | Lalit Aditya | Testing | Completed | 1
US-41 | T-40 | Prepare Technical Documentation | 2026-10-13 | 2026-10-14 | Lalit Aditya | Documentation | Completed | 2
US-42 | T-41 | Prepare Final Project Report | 2026-10-14 | 2026-10-15 | Lalit Aditya | Documentation | Completed | 2
US-43 | T-42 | Prepare Final Demonstration | 2026-10-15 | 2026-10-15 | Lalit Aditya | Demonstration | Completed | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-08-20 | No major impediments | Started implementation of document upload functionality for PDF, DOCX, CSV and TXT files.
Sprint 1 | 2026-08-21 | File validation requirements needed to be finalized | Added file type and input validation.
Sprint 1 | 2026-08-22 | PDF extraction required format-specific handling | Implemented PDF text extraction using PyMuPDF.
Sprint 1 | 2026-08-24 | DOCX tables required additional handling | Implemented DOCX paragraph and table extraction.
Sprint 1 | 2026-08-26 | CSV data needed structured conversion for retrieval | Implemented row-wise CSV parsing and validated extracted content.
Sprint 1 | 2026-08-28 | Chunk size needed to preserve meaningful context | Implemented recursive chunking with configured chunk size and overlap.
Sprint 1 | 2026-08-31 | No major impediments | Completed chunking configuration and started embedding integration.
Sprint 1 | 2026-09-01 | Embedding generation required model integration | Integrated Sentence Transformer model and generated document embeddings.
Sprint 1 | 2026-09-02 | Vector storage configuration required validation | Configured ChromaDB and stored document chunks with embeddings.
Sprint 1 | 2026-09-03 | Retrieval accuracy required validation | Implemented semantic retrieval and validated top-k retrieved document chunks.
Sprint 2 | 2026-09-08 | Agent scope and output structure needed to be defined | Designed the scope and goal extraction agent.
Sprint 2 | 2026-09-09 | Extracting project information from retrieved context required prompt refinement | Implemented scope extraction and deliverable identification.
Sprint 2 | 2026-09-10 | Different document formats contained milestones and dates differently | Added milestone, deadline and important-date extraction.
Sprint 2 | 2026-09-11 | Risk identification required relevant project context | Implemented risk detection using retrieved project information.
Sprint 2 | 2026-09-12 | Dependencies and delivery challenges needed separate identification | Added dependency-gap and delivery-challenge detection.
Sprint 2 | 2026-09-13 | Blockers could appear in both status reports and meeting information | Implemented blocker and unresolved-issue extraction.
Sprint 2 | 2026-09-14 | Pending decisions and action items needed structured extraction | Added pending decision and action-item identification.
Sprint 2 | 2026-09-15 | Agent responses needed a consistent format | Defined structured JSON schemas and integrated them across agents.
Sprint 2 | 2026-09-16 | Agent outputs required validation against project documents | Tested all agents with sample documents and completed validation.
Sprint 3 | 2026-09-17 | Documentation Agent structure needed to be finalized | Defined documentation output structure and agent workflow
Sprint 3 | 2026-09-18 | User story output was not consistently structured | Updated prompt and response parsing
Sprint 3 | 2026-09-19 | Risk register fields were inconsistent | Standardized risk register schema
Sprint 3 | 2026-09-20 | Action items required better extraction from project context | Improved retrieval queries and extraction logic
Sprint 3 | 2026-09-22 | Health score dimensions needed defined scoring criteria | Defined scope, timeline, risk and blocker health dimensions
Sprint 3 | 2026-09-23 | Missing context affected health analysis | Added handling for unavailable context
Sprint 3 | 2026-09-24 | Timeline information required normalization | Improved timeline and deadline context retrieval
Sprint 3 | 2026-09-25 | Health scores were not consistently numeric | Updated agent prompt to enforce 0–100 scores
Sprint 3 | 2026-09-26 | Assistant API request format mismatch | Corrected frontend request payload
Sprint 3 | 2026-09-27 | Assistant sources were not displayed correctly | Updated source response mapping
Sprint 3 | 2026-09-28 | Assistant response required additional validation | Tested context-grounded responses and source retrieval
Sprint 3 | 2026-09-29 | Scope page displayed fallback text and deliverables displayed generic names | Updated frontend mappings for project_goal, milestone_name, description and date
Sprint 3 | 2026-09-30 | Agent output was displayed as raw JSON | Implemented structured UI cards and completed integration testing
Sprint 4 | 2026-10-01 | Dashboard layout and required project insights needed to be finalized | Defined dashboard sections for health, risks, action items and scope
Sprint 4 | 2026-10-02 | Health score data required frontend integration | Connected health agent response to dashboard
Sprint 4 | 2026-10-03 | Risk information required a concise dashboard representation | Added structured risk summary cards
Sprint 4 | 2026-10-04 | Action items required clear status representation | Added structured action item section
Sprint 4 | 2026-10-05 | Scope information required consistent response mapping | Integrated project goal and major deliverables
Sprint 4 | 2026-10-06 | New documents needed to be processed without affecting existing knowledge | Designed incremental upload workflow
Sprint 4 | 2026-10-07 | Newly uploaded documents needed to be added to the vector database | Integrated document processing with existing RAG pipeline
Sprint 4 | 2026-10-08 | Project insights needed to reflect newly uploaded documents | Added analysis refresh after document upload
Sprint 4 | 2026-10-09 | Complete workflow required validation across frontend and backend | Started end-to-end testing
Sprint 4 | 2026-10-10 | Different document formats required separate validation | Tested PDF, DOCX, CSV and TXT workflows
Sprint 4 | 2026-10-11 | Agent responses required consistency checks | Validated scope, risk, blocker and documentation outputs
Sprint 4 | 2026-10-12 | Conversational workflows required broader test coverage | Tested project-related assistant queries
Sprint 4 | 2026-10-13 | Technical documentation required consolidation | Documented architecture, technologies and implementation
Sprint 4 | 2026-10-14 | Final report required testing and implementation results | Completed project report
Sprint 4 | 2026-10-15 | Final demonstration required complete workflow verification | Completed demonstration preparation and final validation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-20 | 2026-09-03 | Lalit Aditya | Start validating each document format immediately after implementation and document configuration decisions. | Stop postponing testing until the complete ingestion module is finished. | Continue modular development and regular testing of each RAG component. | Validated PDF, DOCX, CSV and TXT parsers and documented chunking and embedding configurations.
2 | Sprint 1 | 2026-08-20 | 2026-09-03 | Lalit Aditya | Start testing retrieval with different project-related queries. | Stop considering successful document ingestion as sufficient validation. | Continue testing the complete ingestion-to-retrieval pipeline. | Tested semantic retrieval using sample project documents and queries.
3 | Sprint 2 | 2026-09-08 | 2026-09-16 | Lalit Aditya | Start defining agent output structures before implementing agent logic and test with incomplete information. | Stop allowing inconsistent agent responses and relying only on ideal project documents. | Continue grounding agent outputs in retrieved project context and refining prompts. | Defined structured JSON outputs and tested scope, deliverable, risk, blocker and action-item agents with sample documents.
4 | Sprint 2 | 2026-09-08 | 2026-09-16 | Lalit Aditya | Start validating relationships between risks, blockers, dependencies and action items. | Stop treating individual agent outputs as completely independent. | Continue modularizing agents for easier testing and maintenance. | Added validation scenarios for risk, blocker and dependency-related information and verified structured responses.
5 | Sprint 2 | 2026-09-08 | 2026-09-16 | Lalit Aditya | Start maintaining reusable test cases for agent validation. | Stop performing only manual one-time checks. | Continue testing agent responses against the original project documents. | Created sample validation cases and verified agent outputs against retrieved source content.
6 | Sprint 3 | 2026-09-17 | 2026-09-30 | Lalit Aditya | Start validating agent response schemas before frontend integration | Stop relying on raw JSON responses during UI development | Continue using RAG-based context retrieval for all project intelligence agents | Added structured response validation and frontend data mapping
7 | Sprint 3 | 2026-09-17 | 2026-09-30 | Lalit Aditya | Start performing API integration testing earlier in the sprint | Stop postponing frontend-backend integration until the final stage | Continue modular development of individual agents | Added API testing during agent implementation
8 | Sprint 3 | 2026-09-17 | 2026-09-30 | Lalit Aditya | Start handling missing or incomplete project information explicitly | Stop assuming every document contains all required project information | Continue documenting defects and resolving them within the sprint | Added missing-context handling to the agents
9 | Sprint 3 | 2026-09-17 | 2026-09-30 | Lalit Aditya | Start maintaining consistent naming conventions between backend and frontend | Stop using inconsistent field names across agent responses | Continue using structured JSON for agent communication | Standardized response fields such as project_goal, milestone_name, description and date
10 | Sprint 4 | 2026-10-01 | 2026-10-15 | Lalit Aditya | Start designing dashboard components around actual agent outputs | Stop displaying raw agent responses directly in the UI | Continue using structured agent responses | Created reusable dashboard components
11 | Sprint 4 | 2026-10-01 | 2026-10-15 | Lalit Aditya | Start testing incremental document updates immediately after implementation | Stop assuming that new documents will automatically integrate correctly | Continue validating the RAG pipeline | Tested new document ingestion and retrieval
12 | Sprint 4 | 2026-10-01 | 2026-10-15 | Lalit Aditya | Start performing end-to-end testing across all supported formats | Stop testing individual components in isolation only | Continue maintaining unit and integration tests | Tested complete PDF, DOCX, CSV and TXT workflows
13 | Sprint 4 | 2026-10-01 | 2026-10-15 | Lalit Aditya | Start preparing technical documentation alongside implementation | Stop postponing documentation until the final stage | Continue maintaining defect and testing records | Updated architecture, testing and project documentation