## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Lalit Aditya | 2026-08-22 | PDF parser was not initially extracting text correctly from some pages. | Sprint 1 | Lalit Aditya | Logical | Updated PDF text extraction and added page-level validation. | 2026-08-23 | Closed | PDF extraction verified with sample documents.
2 | Lalit Aditya | 2026-08-25 | DOCX table content was missing during document extraction. | Sprint 1 | Lalit Aditya | Logical | Added support for extracting text from DOCX tables. | 2026-08-26 | Closed | Paragraph and table extraction validated.
3 | Lalit Aditya | 2026-08-27 | CSV rows were not initially converted into suitable text format for retrieval. | Sprint 1 | Lalit Aditya | Logical | Implemented row-wise CSV conversion with column names and values. | 2026-08-28 | Closed | CSV ingestion tested successfully.
4 | Lalit Aditya | 2026-08-30 | Some retrieved chunks contained incomplete context due to unsuitable chunk boundaries. | Sprint 1 | Lalit Aditya | Logical | Configured recursive chunking with appropriate chunk size and overlap. | 2026-08-31 | Closed | Retrieval context improved.
5 | Lalit Aditya | 2026-09-02 | Semantic retrieval returned less relevant chunks for some queries. | Sprint 1 | Lalit Aditya | Logical | Reviewed query embedding and top-k retrieval configuration. | 2026-09-03 | Closed | Retrieval validated using project-related queries.
6 | Lalit Aditya | 2026-09-09 | Scope agent output was inconsistent for documents with limited project information. | Sprint 2 | Lalit Aditya | Logical | Refined agent instructions to handle missing information without generating unsupported data. | 2026-09-10 | Closed | Scope extraction validated.
7 | Lalit Aditya | 2026-09-11 | Risk agent did not consistently identify dependency-related risks. | Sprint 2 | Lalit Aditya | Logical | Updated risk detection logic and prompts to include dependency gaps and delivery challenges. | 2026-09-13 | Closed | Risk detection tested with sample project documents.
8 | Lalit Aditya | 2026-09-13 | Blocker agent sometimes missed unresolved issues from project status information. | Sprint 2 | Lalit Aditya | Logical | Improved blocker extraction using retrieved project context. | 2026-09-14 | Closed | Blocker identification validated.
9 | Lalit Aditya | 2026-09-15 | Agent responses were returned in different structures. | Sprint 2 | Lalit Aditya | Maintainability | Defined a common structured JSON response format for agents. | 2026-09-16 | Closed | Structured outputs validated across agents.
10 | Lalit Aditya | 2026-09-16 | Some agent outputs required additional validation against source documents. | Sprint 2 | Lalit Aditya | Logical | Added validation scenarios using sample project documents and retrieved context. | 2026-09-16 | Closed | Final agent validation completed.
11 | Lalit Aditya | 2026-09-17 | Documentation Agent did not consistently return the expected structured output | Sprint 3 | Lalit Aditya | Functional | Updated agent prompt and response parsing to enforce structured output | 2026-09-18 | Closed | Output structure validated
12 | Lalit Aditya | 2026-09-19 | User stories were not consistently separated into individual entries | Sprint 3 | Lalit Aditya | Functional | Updated documentation generation logic and output format | 2026-09-20 | Closed | User stories displayed correctly
13 | Lalit Aditya | 2026-09-20 | Risk register fields were returned with inconsistent field names | Sprint 3 | Lalit Aditya | Data Validation | Standardized risk register response fields | 2026-09-21 | Closed | Risk register structure validated
14 | Lalit Aditya | 2026-09-22 | Health calculation failed when one project context was unavailable | Sprint 3 | Lalit Aditya | Functional | Added handling for missing project context | 2026-09-23 | Closed | Missing context handled
15 | Lalit Aditya | 2026-09-24 | Health score dimensions were not consistently returned as numeric values | Sprint 3 | Lalit Aditya | Data Validation | Updated Health Agent prompt to enforce numeric scores from 0–100 | 2026-09-25 | Closed | Score format validated
16 | Lalit Aditya | 2026-09-26 | Assistant API returned validation error because frontend request format did not match backend schema | Sprint 3 | Lalit Aditya | API / Integration | Corrected frontend request to send query and top_k | 2026-09-26 | Closed | API request validated
17 | Lalit Aditya | 2026-09-27 | Assistant source information was not displayed correctly in the frontend | Sprint 3 | Lalit Aditya | UI / Integration | Updated response mapping and source rendering | 2026-09-28 | Closed | Sources displayed correctly
18 | Lalit Aditya | 2026-09-29 | Scope page displayed fallback text instead of the extracted project goal | Sprint 3 | Lalit Aditya | UI / Data Mapping | Updated frontend to read project_goal from the agent response | 2026-09-29 | Closed | Project goal displayed correctly
19 | Lalit Aditya | 2026-09-29 | Deliverables page displayed "Deliverable 1" instead of the actual milestone name | Sprint 3 | Lalit Aditya | UI / Data Mapping | Updated frontend to read milestone_name, description and date | 2026-09-30 | Closed | Milestone details displayed correctly
20 | Lalit Aditya | 2026-09-30 | Agent results were displayed as raw JSON instead of structured UI components | Sprint 3 | Lalit Aditya | UI / Integration | Implemented structured rendering for agent results | 2026-09-30 | Closed | Structured cards implemented
21 | Lalit Aditya | 2026-10-02 | Dashboard did not display health score after agent execution | Sprint 4 | Lalit Aditya | UI / Integration | Corrected health API response mapping | 2026-10-02 | Closed | Health score displayed correctly
22 | Lalit Aditya | 2026-10-03 | Risk summary displayed incomplete risk information | Sprint 4 | Lalit Aditya | UI / Data Mapping | Updated risk response mapping | 2026-10-04 | Closed | Risk information displayed correctly
23 | Lalit Aditya | 2026-10-04 | Action item section did not handle empty results correctly | Sprint 4 | Lalit Aditya | UI / Functional | Added empty-state handling | 2026-10-05 | Closed | Empty state displayed correctly
24 | Lalit Aditya | 2026-10-06 | Incremental upload did not update knowledge base correctly | Sprint 4 | Lalit Aditya | RAG / Integration | Updated document ingestion and vector indexing workflow | 2026-10-08 | Closed | New documents indexed successfully
25 | Lalit Aditya | 2026-10-08 | Newly uploaded document information was not immediately reflected in analysis | Sprint 4 | Lalit Aditya | Functional | Added analysis refresh after incremental upload | 2026-10-09 | Closed | Updated analysis verified
26 | Lalit Aditya | 2026-10-10 | CSV upload produced inconsistent data representation during testing | Sprint 4 | Lalit Aditya | Data Processing | Updated CSV parsing and validation | 2026-10-11 | Closed | CSV processing validated
27 | Lalit Aditya | 2026-10-11 | Dashboard layout was inconsistent between analysis sections | Sprint 4 | Lalit Aditya | UI | Standardized dashboard card and section components | 2026-10-12 | Closed | Consistent layout implemented
28 | Lalit Aditya | 2026-10-12 | Assistant response did not reflect newly uploaded project information | Sprint 4 | Lalit Aditya | RAG / Functional | Re-indexed updated documents and validated retrieval | 2026-10-13 | Closed | Updated context retrieved
29 | Lalit Aditya | 2026-10-13 | Technical documentation was missing updated frontend architecture | Sprint 4 | Lalit Aditya | Documentation | Updated architecture and technology documentation | 2026-10-14 | Closed | Documentation updated
30 | Lalit Aditya | 2026-10-15 | Final demonstration revealed inconsistent result formatting in one dashboard section | Sprint 4 | Lalit Aditya | UI / Integration | Standardized final result rendering | 2026-10-15 | Closed | Final demonstration validated

## Sheet2
Logical
User Interface
Maintainability
Standards
Others